## Slide 1
PROCUREMENT GOVERNANCE
Approval workflow
From procurement planning to final Ministry Management decision
Step-by-step operating guide
Ministry of Agriculture | Procurement Tracking System
Notes: [Sources]
- Brand asset: D:/OneDrive/projects/ministry-procurement-tracker/frontend/src/assets/ministry-logo.png
- Workflow source: user-approved PTS workflow and local application implementation, 12 August 2026.

## Slide 2
EXECUTIVE VIEW
One controlled chain moves every plan to a final decision
02
01–03
PLAN
Officer
Prepare activities
and submit
04
SCREEN
Director
Approve, return
or reject
05–06
ENDORSE
5 members
Independent vote
3 votes decide
07–08
APPROVE
Management
Final approve
or reject
09–13
DELIVER
Officer
Contract, track
and close
CONTROL PRINCIPLE
No purchase proceeds without an approved plan, documented decisions and traceable ownership.
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: user-approved PTS workflow and local application implementation, 12 August 2026.

## Slide 3
STEPS 1–3
The Procurement Officer creates the auditable foundation
03
1
Select an assigned project
Only projects previously assigned to the requester are available.
2
Build the procurement plan
Add activities, methods, estimates, funding and milestone dates.
3
Submit a complete plan
Validation blocks submission when activities or planned dates are missing.
QUALITY GATE
Ready to submit?
✓ Assigned project
✓ Procurement activity
✓ Method and amount
✓ All milestone dates
Why this matters
Planning data becomes the single source for later purchase requests, approvals, contracts and performance tracking.
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: PTS procurement plan validation and assigned-project rules in the local application.

## Slide 4
STEP 4
The Director is the first formal decision gate
04
PROCUREMENT DIRECTOR
Review completeness, strategic fit and readiness for endorsement.
APPROVE
Send to Endorsing Committee
Comment optional
RETURN
Officer corrects and resubmits
Reason required
REJECT
Workflow stops at Director
Reason required
Decision comments become part of the permanent approval history.
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: Director review rules implemented in the PTS backend.

## Slide 5
STEPS 5–6
Five independent votes produce one Endorsing Committee outcome
05
1
MEMBER
2
MEMBER
3
MEMBER
4
MEMBER
5
MEMBER
3 of 5
votes determine
the outcome
3 APPROVAL VOTES
Plan is endorsed and advances to Ministry Management approval.
3 REJECTION VOTES
Plan is rejected by the Endorsing Committee and does not advance.
Every member votes once. Individual decisions and comments remain traceable.
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: five-member Endorsing Committee and 3-vote thresholds implemented in the PTS backend.

## Slide 6
STEPS 7–8
Ministry Management makes the final institutional decision
06
ENTRY CONDITION
The plan has secured at least three Endorsing Committee approvals.
FINAL APPROVAL
Comment is optional
Plan becomes Finally Approved and implementation may begin.
FINAL REJECTION
Reason is mandatory
The system blocks rejection until a reason is entered.
SYSTEM-ENFORCED CONTROL
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: Ministry Management approval and mandatory rejection-reason rules implemented in the PTS backend.

## Slide 7
STEPS 9–13
Final approval converts the plan into controlled delivery
07
09
IMPLEMENT
Begin approved procurement
10
TRACK
Record milestone actuals
11
CONTRACT
Register supplier & contract
12
PAY
Record payments & delivery
13
CLOSE
Complete activity and plan
THE COMPLETE AUDIT TRAIL
Plan → Director decision → Committee votes → Management decision → Contract → Payment → Closure
Outcome: one traceable record from intent to delivery.
MoA Procurement Tracking System • Approval workflow
Notes: [Sources]
- Workflow source: post-approval stage tracking, contract, payment and closure functions in the local PTS application.