## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-81746-GO-RFB / Purchase of spare part andLab equipment for liquid nitrogen Production plant | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 500000 |  |  | Under Implementation | Cleared | [9 empty] | 2018/11/27 | 2018/12/14 | 2018/12/02 | 2019/09/18 |  |  |  | 2019/01/13 |  | 2019/02/12 |  | 2019/02/26 |  | 2019/03/19 |  |  | 2019/09/15
ET-MOLF-186848-GO-RFB / Procurement of Field Artificial Insemination Equipment and Liquid Nitrogen Spare Parts | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 300000 |  |  | Under Implementation | Cleared | [9 empty] | 2020/08/11 | 2020/10/09 | 2020/08/16 |  |  |  |  | 2020/09/27 |  | 2020/10/27 |  | 2020/11/10 |  | 2020/12/01 |  |  | 2021/05/30
ET-MOLF-294614-GO-RFB / Procurement of Three units of Liquid Nitrogen Plants | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Goods | Open - International | N | Single Stage One Envelope |  | 2300000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2022/07/06 | 2023/05/17 | 2022/07/21 | 2023/06/27 |  |  |  | 2022/08/25 | 2023/07/28 | 2022/09/09 | 2023/12/14 | 2022/09/29 | 2024/02/23 | 2022/10/19 | 2024/04/22 |  | 2023/02/16
ET-MOLF-358668-NC-RFB / Procurement of non-consulting services for the preparation of documentary video production on LFSDP achievements | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Non-consulting Services | Open - National | N | Single Stage One Envelope |  | 40000 |  | Request for Bids - Non-consulting Services SPD | Completed | Cleared | [9 empty] | 2023/05/10 | 2023/07/10 | 2023/05/15 |  |  |  |  | 2023/06/14 | 2023/08/08 | 2023/06/24 | 2023/10/05 | 2023/07/09 | 2023/10/11 | 2023/07/30 | 2023/11/21 |  | 2023/10/28 | 2024/04/17
ET-MOLF-328105-GO-RFB / Procurement of works for rehabilitation of Amedguya small ruminant development center. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 1600000 |  | Request for Bids - Small Works SPD (1 envelope process) | Signed | Cleared | [9 empty] | 2023/02/13 | 2023/03/11 | 2023/02/18 |  |  |  |  | 2023/03/20 | 2023/03/31 | 2023/04/04 | 2023/04/10 | 2023/04/18 | 2023/05/09 | 2023/05/09 | 2023/05/16 |  | 2023/11/05
ET-MOLF-397483-GO-RFB / Procurement of Peste des petits (PPR) competition ELISA test kits | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 155000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2023/12/15 | 2024/01/01 | 2023/12/20 |  |  |  | 2024/01/29 | 2024/01/19 | 2024/02/05 | 2024/02/03 | 2024/04/03 | 2024/02/17 | 2024/05/29 | 2024/03/03 | 2024/06/27 |  | 2024/06/01
ET-MOLF-81731-GO-RFB / cold chain equipment (Freezers,Refrigerator,Cold-box,Vaccine carriers) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 1000000 |  |  | Completed | Cleared | [9 empty] | 2018/11/20 | 2018/12/10 | 2018/11/25 |  |  |  |  | 2019/01/06 | 2019/01/14 | 2019/02/05 | 2019/06/21 | 2019/02/19 | 2019/06/24 | 2019/03/12 | 2019/06/24 |  | 2019/09/08 | 2019/10/01
ET-MOLF-326803-GO-RFB / Procurement of Poultry equipment and feeds for out growers and feed processors | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 260000 |  | Request for Bids SPD (Goods) - 1 envelope process | Completed | Cleared | [9 empty] | 2022/11/25 | 2023/01/04 | 2022/11/30 |  |  |  |  | 2022/12/30 | 2023/01/26 | 2023/01/14 | 2023/02/27 | 2023/01/24 | 2023/03/10 | 2023/02/08 | 2023/03/15 |  | 2023/05/09 | 2023/04/07
ET-MOLF-302045-GO-RFB / Procurement of In-calf Heifers through Embryo Transfer Technology | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 150000 |  | Request for Bids SPD (Goods) - 1 envelope process | Terminated | Cleared | [9 empty] | 2022/07/14 | 2022/07/31 | 2022/07/19 |  |  |  |  | 2022/08/30 | 2022/09/08 | 2022/09/29 | 2022/11/15 | 2022/10/13 | 2022/12/08 | 2022/11/03 | 2023/01/12 |  | 2023/05/02 |  | 2023/12/27
ET-MOLF-312617-CW-RFB / Procurement of works for Bishoftu Slaughtering House and Cold room Construction | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 1200000 |  | Request for Bids - Small Works SPD (1 envelope process) | Signed | Cleared | [9 empty] | 2022/09/06 | 2022/12/25 | 2022/09/11 |  |  |  |  | 2022/10/23 | 2023/01/17 | 2022/11/07 | 2023/03/07 | 2022/11/21 | 2023/03/07 | 2022/12/12 | 2023/03/15 |  | 2023/06/10
ET-MOLF-285839-GO-RFB / Procurement of Cold chain equipment (Lot I), Vaccination and Veterinary consumables (Lot II) for Disease Prevention and Control Directorate. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 200000 |  | Request for Bids SPD (Goods) - 1 envelope process | Under Implementation | Cleared | [9 empty] | 2022/05/16 | 2023/02/20 | 2022/05/21 |  |  |  |  | 2022/07/02 |  | 2022/08/01 |  | 2022/08/11 |  | 2022/08/26 |  |  | 2022/10/25
ET-MOLF-LFSDP-BEN-202401-GO-RFB / Procurement of two units of Red meat transportation medium duty Cargo Trucks with loading capacity of 3.5 tones | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 123000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | [9 empty] | 2024/04/29 | 2024/09/26 | 2024/05/04 |  |  |  |  | 2024/06/03 | 2024/10/11 | 2024/06/18 | 2023/10/25 | 2024/07/02 | 2023/10/27 | 2024/07/12 | 2023/11/28 |  | 2024/09/10 | 2023/12/06
ET-MOLF-285837-GO-RFB / Procurement of 10000 doses of Bovine Sexed Semen for Dairy Development Directorate | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 900000 |  | Request for Bids SPD (Goods) - 1 envelope process | Completed | Cleared | [9 empty] | 2022/04/15 | 2022/04/23 | 2022/04/20 |  |  |  |  | 2022/06/01 | 2022/05/24 | 2022/06/06 | 2022/05/30 | 2022/06/11 | 2022/06/07 | 2022/06/16 | 2022/06/13 |  | 2022/08/15 | 2022/11/04
ET-MOA-CERC-COVID-19-G-05-RFB-2020 / purchase of milk safety & quality control materials (20 ¦ Electrical chopper , 92 ¦manual chopper,58 ¦ water trough , 58 ¦ feed trough , 17 ¦ electrical milking machine, 241¦milk can , 298 ¦lactometer ,92¦ lectican ,385 ¦metal bucket ,64 ¦cream can) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 250000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2021/04/30 |  | 2021/05/05 |  |  |  |  | 2021/06/16 |  | 2021/07/16 |  | 2021/07/30 |  | 2021/08/20 |  |  | 2021/11/30
ET-MOLF-385733-CW-RFB / Construction Works for Rehabilitation of remaining works of Holeta Bull-dam Farm | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 450000 |  | Request for Bids - Small Works SPD (1 envelope process) | Completed | Cleared | [9 empty] | 2023/11/20 | 2024/06/18 | 2023/11/25 |  |  |  |  | 2023/12/15 | 2024/07/09 | 2023/12/25 | 2024/08/19 | 2024/01/04 | 2024/09/10 | 2024/01/14 | 2024/09/27 | 2025/04/07 | 2024/02/28 | 2025/04/30
ET-MOLF-397255-GO-RFB / Procurement of Animal Feed (3600 quintals of Feed Concentrate and 15000 bales of animal Hay ) For Holeta, Adeaberga and Wolkite Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 170000 |  | Request for Bids SPD (Goods) - 1 envelope process | Under Implementation | Cleared | [9 empty] | 2023/12/12 | 2024/01/14 | 2023/12/17 |  |  |  | 2025/01/29 | 2024/01/16 | 2024/02/02 | 2024/01/31 | 2024/04/04 | 2024/02/14 | 2024/04/17 | 2024/02/29 |  |  | 2024/04/29
ET-MOLF-307714-GO-RFB / Procurement of 70000 doses of Synchronization Hormone | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 260000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2022/10/12 |  | 2022/10/17 |  |  |  |  | 2022/11/18 |  | 2022/11/28 |  | 2022/12/13 |  | 2022/12/28 |  |  | 2023/05/27
ET-MOLF-406960-GO-RFB / Procurement Poultry Feed Ingredients (750 quintals of Maize, 200 quintals of Soybean Meal, 150 quintals of Noug-seed cake, 250 quintals of wheat middling) for Lead Executives for Livestock and Fishery Resources Development | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 115000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2024/02/15 |  | 2024/02/20 |  |  |  |  | 2024/03/11 |  | 2024/03/26 |  | 2024/04/05 |  | 2024/04/15 |  |  | 2024/05/15
ET-MOLF-319552-GO-RFB / Purchases of Network Accessories for Livestock Management Systems Data Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 100000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2022/11/25 |  | 2022/11/30 |  |  |  |  | 2022/12/30 |  | 2023/01/14 |  | 2023/01/28 |  | 2023/02/18 |  |  | 2023/05/19
ET-MOLF-81743-GO-RFB / Purchasing of 150 Heifers (H&F) and 75 Jersey cows as Genetic Material | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 837225 |  |  | Canceled | Modified/Cleared | [9 empty] | 2018/12/24 |  | 2018/12/29 |  |  |  |  | 2019/02/09 |  | 2019/03/11 |  | 2019/03/25 |  | 2019/04/15 |  |  | 2019/10/12
ET-MOLF-334528-GO-RFB / Procurement of Complete Hyper Converged Infrastructure (HCI) Solution including Server for Livestock Identification and traceability System | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 500000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2023/02/10 | 2023/03/11 | 2023/02/15 |  |  |  |  | 2023/03/29 | 2023/04/12 | 2023/04/28 | 2023/06/05 | 2023/05/12 | 2023/06/06 | 2023/06/02 | 2023/06/27 |  | 2023/11/29
ET-MOLF-LFSDP-BEN-202402-GO-RFB / Procurement of Works for Construction of Livestock market center for manucipality (advance level) For Benishangul LFSDP | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 155000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | [9 empty] | 2024/04/10 | 2024/07/31 | 2024/04/15 |  |  |  |  | 2024/05/10 | 2024/08/29 | 2024/05/20 | 2024/09/11 | 2024/05/30 | 2024/10/12 | 2024/06/14 | 2024/11/04 |  | 2024/09/12 | 2025/04/27
ET-MOLF-186847-CW-RFB / Borhole Drilling for Holeta Bull-dam farm | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 150000 |  |  | Canceled | Modified/Cleared | [9 empty] | 2020/08/05 | 2020/10/07 | 2020/08/10 |  |  |  |  | 2020/09/21 |  | 2020/10/21 |  | 2020/11/04 |  | 2020/11/25 |  |  | 2021/05/24
ET-MOLF-81761-GO-RFB / Artificial insemination equipment | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 600000 |  |  | Completed | Cleared | [9 empty] | 2019/01/10 | 2018/12/14 | 2019/01/15 | 2019/09/18 |  |  |  | 2019/02/26 | 2019/01/14 | 2019/03/28 | 2019/05/20 | 2019/04/11 |  | 2019/05/02 | 2019/07/09 |  | 2019/10/29 | 2019/09/24
ET-MOLF-160175-CW-RFB / Upgrading works of Holeta Bulldam Farm | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage Two Envelope |  | 1000000 |  |  | Signed | Cleared | [9 empty] | 2020/02/25 | 2020/10/27 | 2020/03/01 |  |  |  | 2020/03/13 |  |  | 2020/06/25 | 2020/05/01 | 2020/07/09 | 2020/05/13 | 2020/07/30 | 2020/06/02 |  | 2021/01/26
ET-MOLF-82685-CW-RFB / Rehabilitation Livestock &fisheries/TVET in Afar/Gewane | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage Two Envelope |  | 50000 |  |  | Canceled | Cleared | [9 empty] | 2018/12/12 |  | 2018/12/17 | [6 empty] | 2019/04/12 |  | 2019/04/26 |  | 2019/05/17 |  |  | 2019/11/13
ET-MOA-CERC-COVID-19-G-04-RFB-2020 / procurement of sexed semen for national animals genetics improvement institute(NAGII) . | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Goods | Open - International | N | Single Stage One Envelope |  | 500000 |  | Request for Bids SPD (Goods) - 1 envelope process | Pending Implementation | Cleared | [9 empty] | 2021/06/10 |  | 2021/06/15 |  |  |  |  | 2021/07/05 |  | 2021/07/09 |  | 2021/07/14 |  | 2021/07/20 |  |  | 2021/08/31
ET-MOLF-326809-GO-RFB / Procurement of fishing boats with it's out board engine , fishing gear and twine, fish hatchery and limnological equipment | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 630000 |  | Request for Bids SPD (Goods) - 1 envelope process | Under Implementation | Cleared | [9 empty] | 2022/11/28 | 2023/07/05 | 2022/12/03 |  |  |  |  | 2023/01/02 | 2023/07/25 | 2023/01/17 | 2023/11/01 | 2023/01/31 | 2023/11/13 | 2023/02/15 |  |  | 2023/05/16
ET-MOLF-447391-GO-RFB / Procurement of forage seeds | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 1200000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2024/09/22 | 2024/10/18 | 2024/09/27 |  |  |  |  | 2024/10/22 | 2024/11/11 | 2024/11/11 | 2025/04/29 | 2024/11/25 | 2025/05/22 | 2024/12/10 | 2025/05/29 |  | 2025/01/24
ET-MOLF-233180-CW-RFB / Construction of Water Supply Project for Gewane TVET College Dairy & Forage Development Farm | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 1300000 |  | Request for Bids - Small Works SPD (1 envelope process) | Canceled | Modified/Cleared | [9 empty] | 2021/05/10 |  | 2021/05/15 |  |  |  |  | 2021/06/26 |  | 2021/07/20 |  | 2021/07/26 |  | 2021/08/10 |  |  | 2022/02/06
ET-MOLF-81738-GO-DIR / Vehicles for water bodies for reservoir/Van with insulted for finger link transportation | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 450000 |  |  | Canceled | Modified/Cleared | [9 empty] | 2019/02/12 |  | 2019/02/17 |  |  |  |  | 2019/03/31 |  | 2019/04/30 |  | 2019/05/14 |  | 2019/06/04 |  |  | 2019/12/01
ET-MOLF-82681-CW-RFB / Rehabilitation of the Jersey Farms | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage Two Envelope |  | 200000 |  |  | Signed | Cleared | [9 empty] | 2018/11/01 | 2018/12/26 | 2018/11/06 | [6 empty] | 2019/03/02 | 2019/03/26 | 2019/03/16 | 2019/04/05 | 2019/04/06 | 2019/05/13 |  | 2019/10/03
ET-MOLF-81766-GO-RFB / Purchase of office equipment for regional Lab.for perusing pastoral resilience | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 420000 |  |  | Completed | Cleared | [9 empty] | 2018/11/30 | 2019/11/11 | 2018/12/05 |  |  |  |  | 2019/01/16 | 2019/11/12 | 2019/02/15 | 2020/10/29 | 2019/03/01 | 2020/10/29 | 2019/03/22 | 2020/02/05 |  | 2019/09/18 | 2020/07/30
ET-MOLF-326431-GO-RFB / Procurement of Forage Seeds | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 750000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2022/11/25 | 2022/12/05 | 2022/11/30 |  |  |  |  | 2022/12/30 | 2022/12/30 | 2023/01/14 | 2023/02/28 | 2023/01/28 | 2023/03/10 | 2023/02/12 | 2023/03/22 |  | 2023/05/13
ET-MOLF-424274-GO-RFB / Poultry Slaughtering House Equipment & Tools for Bishoftu Slaughtering House | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 400000 |  | Request for Bids SPD (Goods) - 2 envelope process | Signed | Cleared | [9 empty] | 2024/08/29 | 2024/12/29 | 2024/09/03 |  |  |  | 2025/02/04 | 2024/10/15 | 2025/02/11 | 2024/10/30 | 2025/04/08 | 2024/11/13 | 2025/04/28 | 2024/11/28 | 2025/05/30 |  | 2025/02/26
ET-MOLF-463795-GO-RFB / Procurement of 15 Animal Feed Processing Plant including Installation Services | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 530000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2024/12/02 | 2024/12/10 | 2024/12/07 |  |  |  |  | 2024/12/27 | 2025/01/06 | 2025/01/11 | 2025/03/19 | 2025/01/25 | 2025/04/02 | 2025/02/09 | 2025/04/04 |  | 2025/05/10
ET-MOA-CERC-COVID-19-W-01-RFB-2021 / supply ,commissioning ,installation and constriction of cold room and slaughter house in Deberazete . | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Open - National | N | Single Stage One Envelope |  | 875000 |  | Request for Bids - Small Works SPD (1 envelope process) | Canceled | Modified/Cleared | [9 empty] | 2021/05/11 |  | 2021/05/18 |  |  |  |  | 2021/06/23 |  | 2021/07/23 |  | 2021/08/06 |  | 2021/08/27 |  |  | 2021/12/31
ET-MOLF-288438-GO-RFB / Procurement of 7 Milk Chillers with the capacity of 3000 liters | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 550000 |  | Request for Bids SPD (Goods) - 1 envelope process | Signed | Cleared | [9 empty] | 2022/05/16 | 2024/10/19 | 2022/05/21 |  |  |  |  | 2022/06/20 | 2024/12/02 | 2022/06/30 | 2025/04/15 | 2022/07/01 | 2025/05/12 | 2022/07/21 | 2025/05/31 |  | 2022/11/18
ET-MOLF-376145-GO-RFB / Procurement of 15000 doses of Bovine sexed semen and 100000 doses of synchronization hormone | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 1200000 |  | Request for Bids SPD (Goods) - 1 envelope process | Completed | Cleared | [9 empty] | 2023/08/20 | 2023/09/01 | 2023/08/25 |  |  |  |  | 2023/10/06 | 2023/10/10 | 2023/11/05 | 2023/11/27 | 2023/11/13 | 2023/12/07 | 2023/11/28 | 2023/12/15 |  | 2024/02/26 | 2024/07/04
ET-MOLF-469211-GO-RFB / Procurement of Seine net, Scoop and Hand net, Fishing gears & twine, Fish Hatchery and Limnological equipment for fish Hatchery centers. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - National | N | Single Stage One Envelope |  | 275000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2025/01/16 |  | 2025/01/21 |  |  |  |  | 2025/02/10 |  | 2025/02/25 |  | 2025/03/11 |  | 2025/03/26 |  |  | 2025/04/25
ET-MOLF-294618-GO-RFB / Procurement of 60 Holstein Frisian and 10 Jersey Breeding Bulls | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Open - International | N | Single Stage One Envelope |  | 500000 |  | Request for Bids SPD (Goods) - 1 envelope process | Canceled | Modified/Cleared | [9 empty] | 2022/05/19 |  | 2022/05/29 |  |  |  |  | 2022/07/10 |  | 2022/07/25 |  | 2022/08/09 |  | 2022/08/29 |  |  | 2023/02/25

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-81740-GO-RFB / Supply of Office equipment/ furnitures /tables, chairs, shelf to FEDERAL project coordination unit | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 70000 |  |  | Canceled | Cleared | 2018/11/07 | [6 empty] | 2018/11/26 |  | 2018/12/03 |  | 2018/12/17 |  | 2019/01/07 |  |  | 2019/07/06
ET-MOLF-164666-GO-RFQ / Purchase of Car Seat Covers for National LFSDP vehicles | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 2500 |  |  | Completed | Cleared | 2020/03/19 | 2020/04/20 | [5 empty] | 2020/04/07 | 2020/10/14 | 2020/04/14 | 2020/05/19 | 2020/04/28 | 2020/06/05 | 2020/05/19 | 2020/06/09 |  | 2020/11/15 | 2020/06/14
ET-MOLF-180435-NC-RFQ / Purchases of printing service for a National Feed Strategy Document | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 1000 |  |  | Completed | Cleared | 2020/06/19 | 2020/06/21 | [5 empty] | 2020/07/08 | 2020/06/24 | 2020/07/15 | 2020/07/10 | 2020/07/29 | 2020/07/10 | 2020/08/19 | 2020/07/24 |  | 2021/02/15 | 2020/08/18
ET-MOLF-180433-GO-RFQ / Purchase of Office supplies and Shelves for the Federal LFSDP | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 25000 |  |  | Signed | Cleared | 2020/06/19 | 2020/07/22 | [5 empty] | 2020/07/08 | 2020/08/03 | 2020/07/15 | 2020/10/27 | 2020/07/29 |  | 2020/08/19 | 2020/08/28 |  | 2021/02/15 | 2020/09/08
MOA-CERC-NDRMC-G-12/RFQ/2020 / Purchase of 421,070 units of soap (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 166200 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/04 | 2020/11/06 | 2020/11/05 | 2020/11/09 | 2020/11/06 | 2020/11/10 | 2020/11/08 | 2020/11/17 |  | 2020/11/18 | 2020/12/14
MOA-CERC-NDRMC-G-09/RFQ/2020 / Purchase of 42,107 units of water jog (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 66500 |  |  | Completed | Cleared | 2020/11/03 | 2020/11/02 | [5 empty] | 2020/11/08 | 2020/11/06 | 2020/11/15 | 2020/11/09 | 2020/11/17 | 2020/11/10 | 2020/11/19 | 2020/11/29 |  | 2020/12/08 | 2020/12/16
MOA-CERC-NDRMC-G-02/RFQ/2020 / Procurement of 84,214 units of Blanket (Emergency procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 1330000 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/04 | 2020/11/06 | 2020/11/06 | 2020/11/09 | 2020/11/09 | 2020/11/10 | 2020/11/10 | 2020/11/29 |  | 2020/11/25 | 2020/12/29
ET-MOLF-210904-LFSDP-GAM-GO-RFQ / Purchases of 5 deep freezers for fishery CIGs of Gambela LFSDP | No | IDA-61650 | Linking More Productive Farmers to Markets | Post | Goods | Limited | 5000 |  |  | Completed | Cleared | 2020/12/28 | 2021/01/15 | [5 empty] | 2021/01/05 | 2021/01/15 | 2021/01/12 | 2021/01/27 | 2021/01/18 | 2021/03/05 | 2021/01/19 | 2021/03/10 |  | 2021/01/25 | 2021/03/25
ET-MOLF-265633-GO-RFQ / Purchases of 500 units of Scythe | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 6000 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2021/11/29 | 2021/11/29 | [5 empty] | 2021/12/03 | 2021/11/30 | 2021/12/06 | 2021/12/21 | 2021/12/10 | 2021/12/30 | 2021/12/14 | 2022/01/04 |  | 2022/01/03 | 2022/01/07
ET-MOLF-262287-GO-RFQ / Purchases of 10000 bales of Animal Feed/hay for draught emergency responses of Borena Zone. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 45000 |  | Request for Quotations (Non Bank-SPD) | Canceled | Modified/Cleared | 2021/11/28 | [6 empty] | 2021/12/05 |  | 2021/12/08 |  | 2021/12/12 |  | 2021/12/15 |  |  | 2022/01/13
ET-MOLF-470704-GO-RFQ / Purchases of Poultry Feed Processing Inputs Maize(750quintals, Soybean meal (250 quintals) & Wheat middling ()200 quintals) for Bishoftu Poultry Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 45000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2025/01/14 | [6 empty] | 2025/01/29 |  | 2025/02/05 |  | 2025/02/15 |  | 2025/02/25 |  |  | 2025/03/27
ET-MOLF-153188-GO-RFQ / Procurement of Poultry Equipment (Manual/Fountain Drinkers and Feeders, Gasoline motorized three wheel cargo van & Gasoline Generator) for Regional Poultry Multiplication Centers. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 27000 |  |  | Completed | Cleared | 2020/02/27 | 2020/03/04 | [5 empty] | 2020/03/17 | 2020/06/01 | 2020/03/24 | 2020/06/03 | 2020/04/07 | 2020/05/05 | 2020/04/28 | 2020/05/18 |  | 2020/10/25 | 2020/06/01
ET-MOLF-177280-GO-RFQ / Purchase of Covid-19 protective face masks and sanitizers | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Goods | Limited | 110000 |  |  | Completed | Cleared | 2020/06/04 | 2020/10/29 | [5 empty] | 2020/06/23 | 2020/07/24 | 2020/06/30 | 2020/11/09 | 2020/07/14 | 2020/07/15 | 2020/08/04 | 2020/07/27 |  | 2021/01/31 | 2020/08/11
ET-MOLF-186849-GO-RFQ / procurement of Laptop computers for PPR and Fishery | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 12000 |  |  | Completed | Cleared | 2020/08/04 | 2020/10/07 | [5 empty] | 2020/08/23 | 2020/10/14 | 2020/08/30 | 2020/10/14 | 2020/09/13 | 2020/10/14 | 2020/10/04 | 2020/10/30 |  | 2021/04/02 | 2020/10/30
ET-MOA-CERC-NDRMC-G-01/RFQ/2020 / Procurement of 84214 units of MATT (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 1108000 |  |  | Signed | Cleared | 2020/11/02 | 2020/11/02 |  |  |  |  | 2020/11/05 | 2020/11/04 | 2020/11/06 | 2020/11/05 | 2020/11/09 | 2020/11/06 | 2020/11/10 | 2020/11/10 | 2020/11/24 |  | 2020/11/25
ET-MOA- MOA-CERC-NDRMC-NC-013/RFQ/2020 / Procurement of Transportation Services for Delivery of Non Food Items Procured for NDRMC to be distributed for emergency of flood affected areas of the nations (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 200000 |  |  | Under Implementation | Cleared | 2021/02/22 | 2021/02/10 | [5 empty] | 2021/02/23 | 2021/02/18 | 2021/02/24 | 2021/02/19 | 2021/02/26 | 2021/02/25 | 2021/03/01 |  |  | 2021/03/30
ET-MOLF-235025-GO-RFQ / Purchases of 200 boran heifers for Holeta farm center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 95000 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2021/06/07 | 2021/05/30 | [5 empty] | 2021/06/14 | 2021/05/31 | 2021/06/17 | 2021/06/02 | 2021/06/21 | 2021/06/09 | 2021/06/30 | 2021/06/13 |  | 2021/07/26 | 2021/06/23
ET-MOLF-262303-GO-RFQ / Purchases of Animal feed/Mixed concentrate | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 39000 |  | Request for Quotations (Non Bank-SPD) | Pending Implementation | Cleared | 2021/11/29 | [6 empty] | 2021/12/06 |  | 2021/12/09 |  | 2021/12/13 |  | 2021/12/15 |  |  | 2022/01/09
ET-MOLF-334529-GO-RFQ / Purchases of 100 units of Boran Breed heifers for Bishoftu Development Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 55000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2023/02/06 | 2023/01/10 | [5 empty] | 2023/02/18 | 2023/01/16 | 2023/02/25 | 2023/01/16 | 2023/03/05 | 2023/01/20 | 2023/03/15 | 2023/01/20 |  | 2023/04/14
ET-MOLF-469214-GO-RFQ / Procurement of 25,000 bales of hay with transportation services to Adeaberga (70 km from Addis Ababa) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 39000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | 2025/01/06 | 2025/03/05 | [5 empty] | 2025/01/18 | 2025/03/07 | 2025/01/25 | 2025/04/10 | 2025/02/04 | 2025/04/17 | 2025/02/14 | 2025/04/17 |  | 2025/03/16 | 2025/05/08
ET-MOLF-160363-GO-RFQ / Procurement of Meat Inspection Equipment | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 14000 |  |  | Canceled | Modified/Cleared | 2020/02/24 | [6 empty] | 2020/03/14 |  | 2020/03/21 |  | 2020/04/04 |  | 2020/04/25 |  |  | 2020/10/22
MOA-CERC-NDRMC-G-11/RFQ/2020 / Purchase of 42,107 units of kettle (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 332500 |  |  | Completed | Cleared | 2020/11/03 | 2020/11/02 | [5 empty] | 2020/11/10 | 2020/11/06 | 2020/11/11 | 2020/11/09 | 2020/11/15 | 2020/11/10 | 2020/11/17 | 2020/11/17 |  | 2020/11/24 | 2020/12/24
ET-AFAR-CERC-04/2021-GO-RFQ / Purchases of Restocking Animals | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 114500 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2021/08/24 | 2021/07/02 | [5 empty] | 2021/08/26 | 2021/07/02 | 2021/08/27 | 2021/07/22 | 2021/08/30 | 2021/07/29 | 2021/09/01 | 2021/08/12 |  | 2021/09/14 | 2021/09/09
ET-MOLF-326797-GO-RFQ / Procurement of 100kvA power Generators for Poultry multiplication center(fitche) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 50000 |  | Request for Quotations (Non Bank-SPD) | Under Implementation | Cleared | 2022/11/22 | 2023/03/07 | [5 empty] | 2022/12/07 | 2023/03/09 | 2022/12/12 | 2023/03/13 | 2022/12/22 | 2023/03/28 | 2023/01/01 |  |  | 2023/06/30
ET-MOLF-334526-GO-RFQ / Purchases of Veterinary medicine for Adeaberga sub center of Holeta Agricultural Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 4500 |  | Request for Quotations (Non Bank-SPD) | Pending Implementation | Cleared | 2023/01/31 | [6 empty] | 2023/02/10 |  | 2023/02/17 |  | 2023/02/25 |  | 2023/03/04 |  |  | 2023/04/03
ET-MOLF-285838-GO-RFQ / Purchases of Tablet and Hard disks and camera for LFSDP Kobo tool box software implementation | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 90000 |  | Request for Quotations (Non Bank-SPD) | Canceled | Modified/Cleared | 2022/03/28 | [6 empty] | 2022/04/05 |  | 2022/04/10 |  | 2022/04/16 |  | 2022/04/21 |  |  | 2022/05/21
ET-MOA-CERC-COVID-19-NC-01-RFQ-2020 / procurement of promotion service on consumption of chicken | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 18750 |  |  | Canceled | Modified/Cleared | 2021/04/07 | [6 empty] | 2021/04/12 |  | 2021/04/13 |  | 2021/04/21 |  | 2021/04/27 |  |  | 2021/05/04
ET-MOLF-257073-GO-RFQ / Purchases of Laboratory Consumables for National Animal Health Diagnostic Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 25000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2021/10/08 | [6 empty] | 2021/10/14 |  | 2021/10/17 |  | 2021/10/21 |  | 2021/11/05 |  |  | 2021/12/20
ET-MOLF-81734-GO-RFQ / Purchasing of semen of H&F and Jersey to Enhance Production of Exotic Genetic Material. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 15000 |  |  | Signed | Cleared | 2018/10/23 | 2019/01/16 | [5 empty] | 2018/11/11 | 2018/11/30 | 2018/11/18 | 2018/12/21 | 2018/12/02 | 2019/05/15 | 2018/12/23 | 2019/07/19 |  | 2019/06/21
ET-MOLF-81754-GO-RFQ / ppr vaccination equipment &material | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 20000 |  |  | Under Implementation | Cleared | 2018/10/31 | [6 empty] | 2018/11/19 |  | 2018/11/26 |  | 2018/12/10 |  | 2018/12/31 |  |  | 2019/06/29
ET-MOLF-168185-GO-RFQ / Purchase of Generator Accessories for NAHDIC | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 18000 |  |  | Completed | Cleared | 2020/04/17 | 2020/04/21 | [5 empty] | 2020/05/06 | 2020/04/30 | 2020/05/13 | 2020/08/20 | 2020/05/27 | 2020/05/22 | 2020/06/17 | 2020/05/26 |  | 2020/12/14 | 2020/06/05
MOA-CERC-NDRMC-G-07/RFQ/2020 / purchase of 42,107 units of ladle (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 166000 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/03 | 2020/11/06 | 2020/11/04 | 2020/11/09 | 2020/11/06 | 2020/11/10 | 2020/11/08 | 2020/11/29 |  | 2020/11/16 | 2020/12/25
MOA-CERC-NDRMC-G-08/RFQ/2020 / purchase of 42,107 units of wash basin (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 498600 |  |  | Signed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/08 | 2020/11/06 | 2020/11/15 | 2020/11/09 | 2020/11/15 | 2020/11/10 | 2020/11/23 | 2020/11/18 |  | 2020/12/01
MOA-CERC-NDRMC-G-03/RFQ/2020 / Procurement of 40 units of TENT ¦(Rub-hall 10 X 24) (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 868500 |  |  | Signed | Cleared | 2020/11/02 | 2020/11/02 |  |  |  |  | 2020/11/05 | 2020/11/05 | 2020/11/06 | 2020/11/10 | 2020/11/09 | 2020/11/11 | 2020/11/10 | 2020/11/12 | 2020/11/30 |  | 2020/11/27
ET-MOLF-220727-GO-RFQ / procurement of 24 units pf laptops and 10 units of hard disk 1TB for LITS(livestock identification and traceability system ) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 27000 |  |  | Completed | Cleared | 2021/04/05 | 2021/06/18 | [5 empty] | 2021/04/09 | 2021/06/15 | 2021/04/12 | 2021/06/23 | 2021/04/13 | 2021/07/29 | 2021/04/19 | 2021/08/12 |  | 2021/04/30 | 2021/09/07
ET-AFAR-CERC-002/2021-GO-RFQ / Purchases of Animal feed/concentrate for Afar regional State | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 640000 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2021/08/24 | 2021/07/02 | [5 empty] | 2021/08/26 | 2021/07/02 | 2021/08/27 | 2021/07/22 | 2021/08/30 | 2021/07/29 | 2021/09/01 | 2021/08/12 |  | 2021/09/14 | 2021/09/09
ET-AFAR-CERC-001/2021-GO-RFQ / Purchases of Non-consulting service for transportation service of Animal feed/hay in Afar regional State | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 41000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2021/08/24 | 2021/07/02 | [5 empty] | 2021/08/26 | 2021/07/02 | 2021/08/27 | 2021/07/22 | 2021/08/30 | 2021/07/29 | 2021/09/01 | 2021/08/12 |  | 2021/09/15
ET-MOLF-285809-GO-RFQ / Purchases of Semen Laboratory Reagent for National Animal Genetics Improvement Institute | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 55000 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2022/03/24 | 2022/05/18 | [5 empty] | 2022/04/03 | 2022/05/18 | 2022/04/06 | 2022/05/26 | 2022/04/11 | 2022/06/15 | 2022/04/16 | 2022/06/29 |  | 2022/05/31 | 2022/08/23
ET-MOLF-307669-GO-RFQ / Purchases of IVF/Ultrasonic Equipment for Oocyte Collection | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 60000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2022/08/10 | 2022/07/01 | [5 empty] | 2022/08/20 | 2022/07/06 | 2022/08/25 | 2022/07/08 | 2022/09/04 | 2022/07/12 | 2022/09/14 | 2022/07/12 |  | 2022/11/13
ET-MOLF-348918-GO-RFQ / Procurement of Concentrate for Adeberga Livestock Research center & Wolkite Livestock Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 65000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2023/05/01 | 2023/07/13 | [5 empty] | 2023/05/13 | 2023/07/14 | 2023/05/20 | 2023/07/25 | 2023/05/25 | 2023/08/01 | 2023/06/15 | 2023/08/01 |  | 2023/07/15
ET-MOLF-328119-GO-RFQ / Purchases of construction materials for National Fishery and Aquatic Life Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 90000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2023/01/31 | 2023/11/27 | [5 empty] | 2023/02/15 | 2024/12/02 | 2023/02/22 | 2023/12/11 | 2023/03/04 | 2023/12/18 | 2023/03/09 | 2023/12/18 |  | 2023/04/23
ET-MOLF-339282-NC-RFQ / Purchases of printing services of office supplies with LFSDP Logo | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 15000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Pending Implementation | Cleared | 2023/01/31 | [6 empty] | 2023/02/10 |  | 2023/02/15 |  | 2023/02/20 |  | 2023/02/25 |  |  | 2023/03/17
MOA-LFSDP/CERC2-G3/RFQ/2023 / Procurement of Forage Seeds for Oromia, Somali and Southern Nations and Nationalities of Peoples for Drought | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 1650000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2023/04/10 | 2023/05/10 | [5 empty] | 2023/04/16 | 2023/05/12 | 2023/04/19 | 2023/05/14 | 2023/04/22 | 2023/05/30 | 2023/04/25 | 2023/05/30 |  | 2023/05/10
ET-MOLF-427037-GO-RFQ / Procurement of one unit of Animal Feed processing plant for Benishangul LFSDP | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 97000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | 2024/05/14 | 2024/05/24 | [5 empty] | 2024/06/02 | 2024/05/27 | 2024/06/09 | 2024/05/30 | 2024/06/23 | 2024/06/03 | 2024/07/08 | 2024/06/04 |  | 2024/09/06 | 2024/09/20
ET-MOLF-262297-GO-RFQ / Purchases of Audio-visual equipment for the federal LFSDP | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 73000 |  | Request for Quotations (Non Bank-SPD) | Canceled | Modified/Cleared | 2021/11/29 | [6 empty] | 2021/12/05 |  | 2021/12/08 |  | 2021/12/12 |  | 2021/12/15 |  |  | 2022/01/09
ET-MOA-CERC-FLOOD-G-04/RFQ/2020 / procurement of 4000 quintals of forage seed (emergency procurement for flood crisis mitigation) for Amhara, Somali and Oromia regions. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 600000 |  |  | Canceled | Modified/Cleared | 2021/01/15 | [6 empty] | 2021/01/20 |  | 2021/01/25 |  | 2021/01/27 |  | 2021/01/29 |  |  | 2021/02/12
ET-MOLF-210902-LFSDP-GAM-GO-RFQ / Purchase of office supplies for Abobo Woreda of Gambela LFSDP Office in four lots (lot-1 purchase of IT equipment &related items lot-2 purchase of office furniture supplies lot-3 purchase of Electronics and lot -4 purchase of Generators | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 30000 |  |  | Completed | Cleared | 2020/12/21 | 2020/12/09 | [5 empty] | 2020/12/25 | 2020/12/10 | 2020/12/28 | 2020/12/10 | 2020/12/30 | 2020/12/11 | 2021/01/05 | 2020/12/19 |  | 2021/01/12 | 2020/12/19
MOA-CERC-RE-BID-NDRMC-G-04/RFQ/2020 / Procurement of 84,214 units of Plastic Sheet (4 X 5) (Emergency Procurement for National Disaster and Risk Mitigation Commission | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 1350000 |  |  | Signed | Cleared | 2021/01/15 | 2021/07/02 | [5 empty] | 2021/01/20 | 2021/07/05 | 2021/01/22 | 2021/07/20 | 2021/01/25 | 2021/07/26 | 2021/01/27 | 2021/08/10 |  | 2021/02/08
ET-MOLF-210903-LFSDP-GAM-NC-RFQ / Maintenance service & supply of related items for Abobo wereda LFSDP office, Gambela | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Limited | 18000 |  |  | Completed | Cleared | 2021/01/15 | 2021/07/06 | [5 empty] | 2021/02/03 | 2021/07/07 | 2021/02/10 | 2021/07/07 | 2021/02/24 | 2021/07/07 | 2021/03/17 | 2021/07/11 |  | 2021/09/13 | 2021/08/14
MOA-CERC-NDRMC-G-04/RFQ/2020 / Procurement of 84,214 units of Plastic Sheet (4 X 5) (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 1330000 |  |  | Signed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/05 | 2020/11/06 | 2020/11/12 | 2020/11/09 | 2020/11/13 | 2020/11/10 | 2020/11/16 | 2020/11/29 |  | 2020/11/30 |  | 2021/01/25
MOA-CERC-NDRMC-G-06/RFQ/2020 / Purchase of 84214 units of cup (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 199500 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/05 | 2020/11/06 | 2020/11/06 | 2020/11/09 | 2020/11/09 | 2020/11/10 | 2020/11/11 | 2020/11/29 |  | 2020/11/25 | 2020/12/27
ET-AFAR-CERC-03/2021-GO-RFQ / Purchases of Purchases of Veterinary Drugs for Afar regional State | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 37500 |  | Request for Quotations (Non Bank-SPD) | Completed | Cleared | 2021/08/24 | 2021/07/02 | [5 empty] | 2021/08/26 | 2021/07/02 | 2021/08/27 | 2021/07/22 | 2021/08/30 | 2021/07/29 | 2021/09/01 | 2021/08/12 |  | 2021/09/13 | 2021/09/09
ET-MOLF-262282-GO-RFQ / Purchases of 100 Borana Breed Heifers for Wolkite Research center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 43000 |  | Request for Quotations (Non Bank-SPD) | Under Implementation | Cleared | 2021/11/30 | 2021/11/24 | [5 empty] | 2021/12/04 |  | 2021/12/09 |  | 2021/12/11 |  | 2021/12/14 |  |  | 2022/01/13
ET-MOLF-350281-GO-RFQ / Purchases of Poultry Equipment for Model Poultry Program | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 16000 |  | Request for Quotations (Non Bank-SPD) | Under Implementation | Cleared | 2023/05/02 | 2023/03/01 | [5 empty] | 2023/05/12 | 2023/03/10 | 2023/05/19 | 2023/03/17 | 2023/05/26 | 2023/03/23 | 2023/05/31 |  |  | 2023/06/15
ET-MOLF-445876-GO-RFQ / Laboratory machinery, tools and equipment’s | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 98000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2024/08/21 | 2024/10/16 | [5 empty] | 2024/08/31 | 2024/10/18 | 2024/09/05 | 2024/12/17 | 2024/09/15 | 2024/12/17 | 2024/09/25 | 2024/12/17 |  | 2024/11/09
ET-MOA-CERC-COVID-19-W-03-RFQ-2020 / building of Addis Ababa market outlet for poultry . | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Limited | 45000 |  |  | Canceled | Modified/Cleared | 2021/04/06 | [6 empty] | 2021/04/11 |  | 2021/04/13 |  | 2021/04/20 |  | 2021/04/27 |  |  | 2021/06/27
ET-MOA-CERC-COVID-19-W-04-RFQ-2020 / building of cold room for eggs in Hawasa ,Bahirdar and Mekele. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Limited | 100000 |  |  | Canceled | Modified/Cleared | 2021/04/06 | [6 empty] | 2021/04/12 |  | 2021/04/17 |  | 2021/04/25 |  | 2021/05/02 |  |  | 2021/05/24
ET-MOLF-302056-GO-RFQ / Purchases of construction materials (Square pipe Metal, Plywood (MDF), Electrode, Viner and Glue) for Batu Fishery Center. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 65000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2022/07/15 | [6 empty] | 2022/07/25 |  | 2022/08/01 |  | 2022/08/15 |  | 2022/08/30 |  |  | 2022/10/14
ET-MOLF-160179-NC-RFB / Procurement of Office rent and maintenance services for the Federal LFSDP | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Non-consulting Services | Limited | 275000 |  |  | Signed | Cleared | 2020/02/24 | 2020/10/07 | [5 empty] | 2020/03/14 | 2020/03/05 | 2020/03/21 | 2020/03/10 | 2020/04/04 | 2020/03/12 | 2020/04/25 | 2020/03/25 |  | 2020/10/22
ET-MOLF-213651-GO-RFQ / Procurement of Extenders and insemination for National Animals Genetics Improvement Institute | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 64000 |  |  | Completed | Cleared | 2021/01/18 | 2021/02/05 | [5 empty] | 2021/01/22 | 2021/02/08 | 2021/01/26 | 2021/02/24 | 2021/01/29 | 2021/03/03 | 2021/02/04 | 2021/03/19 |  | 2021/02/28 | 2021/06/02
MOA-CERC-NDRMC-G-10/RFQ/2020 / Purchase of 42,107 units of cooking pot (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 665000 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/04 | 2020/11/06 | 2020/11/08 | 2020/11/09 | 2020/11/09 | 2020/11/10 | 2020/11/11 | 2020/11/29 |  | 2020/11/22 | 2020/12/25
ET-MOA-CERC-FLOOD-G-01/RFQ/2020 / Procurement of 7000 tones (or 35,000 bale) feed/hay (Emergency procurement for Flood crisis Mitigation) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 400000 |  |  | Completed | Cleared | 2020/11/16 | 2020/11/17 | [5 empty] | 2020/11/17 | 2020/12/18 | 2020/11/20 | 2020/12/18 | 2020/11/23 | 2020/12/23 | 2020/11/24 | 2021/01/11 |  | 2020/12/16 | 2021/02/13
ET-MOLF-81745-GO-RFB / Livestock identification Tractability equipment & computer | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 80000 |  |  | Canceled | Cleared | 2019/02/06 | [6 empty] | 2019/02/25 |  | 2019/03/04 |  | 2019/03/18 |  | 2019/04/08 |  |  | 2019/10/05
ET-MOLF-307671-GO-RFQ / Purchases of 50 units of Liquid Nitrogen Containers for Livestock Development Institute (National Animal Genetics Institute) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 57000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2022/08/09 | 2022/07/27 | [5 empty] | 2022/08/19 | 2022/07/28 | 2022/09/02 | 2022/08/02 | 2022/09/05 | 2022/08/09 | 2022/09/15 | 2022/08/09 |  | 2022/11/14
ET-MOLF-397268-GO-RFQ / Purchases of Livestock farm maintaining tools | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 50000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | 2024/01/05 | 2024/03/05 | [5 empty] | 2024/01/18 | 2024/03/07 | 2024/01/23 | 2024/03/29 | 2024/02/02 | 2024/04/03 | 2024/02/07 | 2024/04/03 |  | 2024/03/08 | 2024/05/01
ET-MOLF-445837-GO-RFQ / Purchases of Construction materials for National Fishery and Aquatic Life Research Center and Bishoftu Livestock Development Institute | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 75000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2024/08/27 | 2024/10/30 | [5 empty] | 2024/09/11 | 2024/11/05 | 2024/09/18 | 2024/12/11 | 2024/09/28 | 2024/12/17 | 2024/10/08 | 2024/12/17 |  | 2024/10/11
ET-MOLF-445842-GO-RFQ / Purchases of veterinary equipment and drugs for Bishoftu Livestock Development Institute. (2 Hoof trimmin Machine(Electrical), 2 electrical dehorning, 10 Calf Milk, 2 Veterinary obstatrical kit, 2 Hoof triming (Manual, 2 Hoof knif (Manual, 10 Algun With C | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 15000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2024/08/20 | [6 empty] | 2024/08/26 |  | 2024/09/02 |  | 2024/09/09 |  | 2024/09/19 |  |  | 2024/10/19
ET-MOA-CERC-COVID-19-W-02-RFQ-2020 / procurement of borehole drilling for poultry cold room and slaughter house in Debrezayte | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Works | Limited | 165000 |  |  | Canceled | Modified/Cleared | 2021/02/26 | [6 empty] | 2021/03/17 |  | 2021/03/24 |  | 2021/04/07 |  | 2021/04/28 |  |  | 2021/10/25
ET-MOA-CERC-COVID-19-G-01-RFQ-2021 / procurement of 2350 quintal of layer feed | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 65000 |  |  | Canceled | Modified/Cleared | 2021/04/05 | [6 empty] | 2021/04/12 |  | 2021/04/13 |  | 2021/04/16 |  | 2021/04/17 |  |  | 2021/04/30
ET-MOLF-180432-GO-RFQ / Purchase of Semen Laboratory Reagent (Extenders & consumables) for NAGI | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 55000 |  |  | Completed | Cleared | 2020/06/19 | 2020/06/25 | [5 empty] | 2020/07/08 | 2020/07/05 | 2020/07/15 | 2020/08/05 | 2020/07/29 | 2020/08/10 | 2020/08/19 | 2020/08/23 |  | 2021/02/15 | 2020/09/01
ET-MOLF-213648-GO-RFQ / Procurement of Peste des petits ruminants (PPR) Kits and consumables for National Animal Health Diagnostic and Investigation Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 52000 |  |  | Signed | Cleared | 2021/01/15 | 2021/01/27 | [5 empty] | 2021/01/21 | 2021/01/28 | 2021/01/25 | 2021/02/24 | 2021/01/29 | 2021/03/03 | 2021/02/02 | 2021/03/19 |  | 2021/02/25
MOA-CERC-NDRMC-G-05/RFQ/2020 / procurement of 84,214 units of plates (Emergency Procurement for National Disaster and Risk Mitigation Commission) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 221600 |  |  | Completed | Cleared | 2020/11/02 | 2020/11/02 | [5 empty] | 2020/11/06 | 2020/11/06 | 2020/11/09 | 2020/11/09 | 2020/11/10 | 2020/11/10 | 2020/11/16 | 2020/11/18 |  | 2020/11/30 | 2020/12/04
ET-MOA-CERC-COVID-19-G-01/RFQ/2020 / Procurement of 13 Milk Transportation Truck (Emergency procurement for Covid-19 mitigation purpose) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 684200 |  |  | Completed | Cleared | 2020/11/10 | 2021/09/24 | [5 empty] | 2020/11/13 | 2021/09/24 | 2020/11/14 | 2021/09/27 | 2020/11/16 | 2021/09/27 | 2020/11/20 | 2021/09/28 |  | 2020/12/20 | 2023/01/12
ET-MOLF-285963-GO-RFQ / Purchases of Poultry equipment for Poultry Development Directorate | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 17000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared | 2022/03/30 | 2022/01/10 | [5 empty] | 2022/04/09 | 2022/01/13 | 2022/04/16 | 2022/02/16 | 2022/04/21 | 2022/03/03 | 2022/04/26 | 2022/03/03 |  | 2022/05/26
MOA-LFSDP/CERC2-G1/RFQ/2023 / Procurement of Veterinary drugs for Southern Nations and Nationalities of Peoples, Somali and Oromia for Drought Emergency Response | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 750000 |  | Request for Quotations (Non Bank-SPD) | Signed | Cleared |  |  | 2023/04/13 | [8 empty] | 2023/04/22 | 2023/07/31 | 2023/04/25 | 2023/07/31 |  | 2023/05/10
MOA-LFSDP/CERC2-G4/RFQ/2023 / Procurement of 33,000 bales of Animal Feed hay/ including transportation Southern Nations and Nationalities of Peoples for Drought Emergency Response | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 225000 |  | Request for Quotations (Non Bank-SPD) | Under Implementation | Cleared | 2023/04/10 | 2023/05/10 | [5 empty] | 2023/04/16 | 2023/05/12 | 2023/04/19 | 2023/05/15 | 2023/04/22 | 2023/05/31 | 2023/04/25 |  |  | 2023/05/05
ET-MOLF-334537-GO-RFQ / Purchases of two units of laptops and two units of tablets for Animal Health veterinary public health Lead Executives and Livestock and fisheries sector state minister office | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 13000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2023/02/08 | 2023/01/20 | [5 empty] | 2023/02/18 | 2023/01/24 | 2023/02/25 | 2023/01/25 | 2023/03/07 | 2023/02/22 | 2023/03/12 | 2023/02/22 |  | 2023/04/11
ET-MOLF-445838-GO-RFQ / Purchases of Animal Feed processing input for Bishoftu Livestock Development Institute (135 quintals of Maize, 165 quintals of Noug cake, 16 quintals of salt, 11 quintals of primix, 143 quintals of wheat bran, 104 quintals of wheat middling) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited - National | 25000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2024/08/20 | 2024/09/16 | [5 empty] | 2024/08/30 | 2024/09/25 | 2024/09/06 | 2024/10/15 | 2024/09/20 | 2024/10/21 | 2024/09/30 | 2024/10/21 |  | 2024/10/30
ET-MOA-CERC-COVID-19-G-02/RFQ/2020 / Procurement of Milk Chiller | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 295200 |  |  | Canceled | Modified/Cleared | 2020/11/17 | [6 empty] | 2020/11/20 |  | 2020/11/23 |  | 2020/11/24 |  | 2020/11/25 |  |  | 2020/12/25
ET-MOA-CERC-FLOOD-G-05/RFQ/2020 / procurement of animal feed/concentrates | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 500000 |  |  | Canceled | Modified/Cleared | 2021/02/12 | [6 empty] | 2021/02/16 |  | 2021/02/17 |  | 2021/02/19 |  | 2021/02/22 |  |  | 2021/03/08
ET-MOLF-257059-NC-RFQ / Non-consulting service for maintenance of Heavy duty Generator for DbreZeit, Fiche & Nekemt Poultry Multiplication Centers | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Limited | 23500 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2021/10/08 | [6 empty] | 2021/10/15 |  | 2021/10/19 |  | 2021/10/24 |  | 2021/10/27 |  |  | 2021/11/21
MOA-LFSDP/CERC2-G2/RFQ/2023 / Procurement of 2000 quintals of Animal Feed/concentrate including transportation to Oromia; Borena zone, for Drought Emergency response | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 160000 |  | Request for Quotations (Non Bank-SPD) | Canceled | Modified/Cleared | 2023/04/07 | [6 empty] | 2023/04/15 |  | 2023/04/18 |  | 2023/04/23 |  | 2023/04/28 |  |  | 2023/05/18
ET-MOA-CERC-COVID -19-G-06-RFQ-2020 / procurement of COVID -19 protective materials (18,000 units of face mask, 28,200 units of hand glove , 450 litters of hand sanitizer and 450 litters of alcohol ) for dairy and poultry | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Goods | Limited | 40000 |  |  | Under Implementation | Cleared | 2021/04/06 | 2021/04/16 | [5 empty] | 2021/04/12 |  | 2021/04/13 |  | 2021/04/15 |  | 2021/04/22 |  |  | 2021/05/11
ET-MOLF-220728-GO-RFQ / procurement of laboratory equipment and consumables for national animal health diagnostic and investigation centre | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 35000 |  |  | Under Implementation | Cleared | 2021/04/06 | 2021/04/16 | [5 empty] | 2021/04/11 |  | 2021/04/14 |  | 2021/04/20 |  | 2021/05/10 |  |  | 2021/05/19
ET-MOA-CERC-COVID-19-G-03/RFQ/2020 / Procurement of 70000 dose of Synchronization Hormone | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 104100 |  |  | Completed | Cleared | 2020/11/17 | 2020/11/17 | [5 empty] | 2020/11/21 | 2020/11/19 | 2020/11/24 | 2020/12/09 | 2020/11/25 | 2021/01/13 | 2020/11/26 | 2021/01/25 |  | 2020/12/28 | 2021/05/29
ET-MOA-CERC-FLOOD-G-03/RFQ/2020 / Procurement of 25000 bales of Animal Feed/hay | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 350000 |  |  | Signed | Cleared | 2020/11/16 | 2021/10/15 | [5 empty] | 2020/11/19 | 2021/12/15 | 2020/11/21 | 2021/10/18 | 2020/11/23 | 2021/10/21 | 2020/11/25 | 2021/10/26 |  | 2020/12/10
ET-MOLF-210905-LFSDP-GAM-GO-RFQ / Purchases of five Generators & twenty units of Ice box for fihsery CIGs of Gambella LFSDP | No | IDA-61650 | Linking More Productive Farmers to Markets | Post | Goods | Limited | 9000 |  |  | Under Implementation | Cleared | 2020/12/30 | 2021/02/03 | [5 empty] | 2021/01/05 | 2021/02/03 | 2021/01/08 | 2021/02/12 | 2021/01/11 | 2021/02/15 | 2021/01/13 |  |  | 2021/01/22
ET-MOLF-235026-GO-RFQ / Purchases of 250 Breeding heifers(150 fogera breeds for Chagini farm center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 90000 |  | Request for Quotations (Non Bank-SPD) | Canceled | Cleared | 2021/05/25 | [6 empty] | 2021/06/04 |  | 2021/06/08 |  | 2021/06/14 |  | 2021/06/18 |  |  | 2021/07/23
ET-MOLF-302053-GO-RFQ / Purchases of Poultry Feed Processing Inputs (750 Quintals of Maize) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 55000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Signed | Cleared | 2022/07/04 | 2022/06/10 | [5 empty] | 2022/07/14 | 2022/06/20 | 2022/07/21 | 2022/06/25 | 2022/08/04 | 2022/06/27 | 2022/08/19 | 2022/06/27 |  | 2022/10/03
ET-MOLF-160373-GO-RFB / Procurement of Newcastle disease Virus and PPR Equipment & Consumables | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 35000 |  |  | Canceled | Modified/Cleared | 2020/02/27 | [6 empty] | 2020/03/17 |  | 2020/03/24 |  | 2020/04/07 |  | 2020/04/28 |  |  | 2020/10/25
ET-MOA-CERC-FLOOD-G-02/RFQ/2020 / Purchase of Veterinary drugs and livestock vaccine (Emergency procurement for Flood crisis Mitigation) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Limited | 227800 |  |  | Canceled | Modified/Cleared | 2020/11/11 | [6 empty] | 2020/11/14 |  | 2020/11/16 |  | 2020/11/18 |  | 2020/11/20 |  |  | 2020/12/04

## DIR
Direct Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-153186-GO-DIR / procurement of Koekoek parent stock for regional poultry multiplication centers | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct | 3000 |  |  | Pending Implementation | Cleared | 2020/01/13 |  | 2020/01/13 |  | 2020/01/15 |  | 2020/01/16 |  | 2020/01/21 |  |  | 2020/01/31
ET-MOLF-334533-GO-DIR / Purchases of 15 Semen Producing Domestic Bulls for Livestock Development Institute. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct - National | 25000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Completed | Cleared | 2023/01/31 | 2023/01/25 | 2023/02/05 | 2024/02/26 | 2023/02/10 | 2024/02/23 | 2023/02/24 | 2024/03/27 | 2023/03/06 | 2024/03/27 |  | 2023/04/05 | 2024/04/18
ET-MOLF-46836-GO-DIR / Procurement of 7452 mountain bike | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Goods | Direct | 1043280 |  |  | Canceled | Cleared | 2018/02/12 |  | 2018/02/17 |  | 2018/02/17 |  | 2018/03/03 |  | 2018/03/24 |  |  | 2020/03/23
ET-MOA-CERC-FLOOD-G-01/DIR/2020 / Procurement of 3,445 tons of wheat seed (Emergency procurement for Flood crisis Mitigation) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct | 2000000 |  |  | Completed | Cleared | 2020/11/16 | 2020/12/01 | 2020/11/17 | 2020/12/01 | 2020/11/19 | 2020/12/17 | 2020/11/23 | 2020/12/17 | 2020/11/25 | 2020/12/23 |  | 2020/12/14 | 2021/01/17
ET-MOLF-253928-NC-DIR / Non-Consulting service for maintenance of Hatchery Equipment for Debrezeit Animal Research Center | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Non-consulting Services | Direct | 30000 |  | Other (with field for explanation) | Canceled | Modified/Cleared | 2021/11/30 |  | 2021/12/03 |  | 2021/12/07 |  | 2021/12/10 |  | 2021/12/13 |  |  | 2022/01/12
ET-MOLF-46832-GO-DIR / Procurement of 378 Motorcycles through UNOPS | No | IDA-61650 | Strengthening National Institutions and Programs,Project Coordination, Monitoring and Evaluation, and Knowledge Management | Prior | Goods | Direct | 1216560 |  |  | Canceled | Cleared | 2018/02/12 |  | 2018/02/17 |  | 2018/02/17 |  | 2018/03/03 |  | 2018/03/24 |  |  | 2018/09/20
ET-MOLF-302038-GO-RFB / Procurement of Liquid Nitrogen Spare Parts | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct - National | 95000 |  | Other (with field for explanation) | Canceled | Modified/Cleared | 2022/10/17 |  | 2022/10/22 |  | 2022/10/27 |  | 2022/11/10 |  | 2022/12/01 |  |  | 2023/03/01
ET-MOA-CERC-FLOOD-G-02/DIR/2021 / Procurement of 2000 tons of wheat seed for emergency procurement of flood Reponses . | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct | 1400000 |  |  | Signed | Cleared | 2021/02/12 | 2021/03/05 | 2021/02/12 | 2021/03/08 | 2021/02/15 | 2021/04/06 | 2021/02/17 | 2021/04/12 | 2021/02/22 | 2021/04/19 |  | 2021/03/09
ET-MOLF-421192-GO-DIR / Procurement of In-calf Heifers Developed through Embryo Transfer Technology | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods | Direct - International | 560000 |  | National Procurement Document - 1 Envelope process (Non Bank-SPD) | Canceled | Modified/Cleared | 2024/05/13 | 2024/05/13 | 2024/05/18 | 2024/06/11 | 2024/05/23 |  | 2024/06/06 |  | 2024/06/21 |  |  | 2025/02/16
ET-MOLF-46827-GO-DIR / Procurement of 8 units of Hard top station wagon, 6 units of long base and 111 units of Double cabin pick up vehicles through UNOPS | No | IDA-61650 | Strengthening National Institutions and Programs,Project Coordination, Monitoring and Evaluation, and Knowledge Management | Prior | Goods | Direct | 5330000 |  |  | Completed | Cleared | 2018/02/12 | 2018/10/02 | 2018/02/17 | 2018/10/19 | 2018/02/17 | 2018/11/07 | 2018/03/12 | 2018/12/03 | 2018/04/02 | 2018/12/05 |  | 2018/09/29 | 2020/01/01

## UN
UN Agencies (Direct) - *All Categories
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-182515-GO-UN / Procurement of 15 Land-cruiser double Cup Vehicles and 300 Motor Cycles | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Goods |  | 3200000 |  |  | Completed | Cleared | 2020/06/30 | 2020/08/14 | 2020/07/05 | 2020/11/19 | 2020/07/05 | 2020/12/23 | 2020/07/19 | 2021/01/07 | 2020/08/09 | 2021/01/16 |  | 2021/02/05 | 2021/09/25
ET-MOLF-201542-GO-UN / Procurement of three Live Fish Carrier Trucks | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Goods |  | 200000 |  |  | Canceled | Cleared | 2020/10/27 |  | 2020/10/30 |  | 2020/11/03 |  | 2020/11/06 |  | 2020/11/10 |  |  | 2021/01/31
ET-MOLF-110841-GO-UN / procurement of 7452 montain Bike | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods |  | 1043280 |  |  | Canceled | Cleared | 2019/04/23 |  | 2019/04/28 |  | 2019/04/28 |  | 2019/05/12 |  | 2019/06/02 |  |  | 2019/11/29
ET-MOLF-103206-CS-UN / Technical support on the following • Livestock and Fisheries Data Analysis and Monitoring System (DAMS • Animal identification and traceability • Strategy and approach for Extension Advisory System (EAS) Good Animal Husbandry Practice GAHP • Performance | No | IDA-61650 | Linking More Productive Farmers to Markets | Prior | Consultant Services |  | 3700000 |  |  | Canceled | Cleared | 2019/04/01 |  | 2019/04/06 |  | 2019/04/06 |  | 2019/04/20 |  | 2019/05/11 |  |  | 2019/11/07
ET-MOLF-213150-GO-UN / procurement of three live fish carrier trucks . | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Goods |  | 200000 |  |  | Signed | Cleared | 2021/01/10 | 2021/02/13 | 2021/01/15 | 2021/02/17 | 2021/01/15 | 2021/04/19 | 2021/01/29 | 2021/04/20 | 2021/02/19 | 2021/05/07 | 2021/12/14 | 2021/08/18
ET-MOLF-81773-GO-DIR / Procurement of 146 Motorcycles | No | IDA-61650 | Strengthening National Institutions and Programs,Project Coordination, Monitoring and Evaluation, and Knowledge Management | Prior | Goods |  | 1569362 |  |  | Completed | Cleared | 2018/11/07 |  | 2018/11/12 |  | 2018/11/12 | 2020/04/07 | 2018/11/26 | 2020/04/09 | 2018/12/17 | 2019/04/01 |  | 2019/06/15 | 2020/04/20

## QCBS - FBS - LCS
Quality and Cost Based Selection (QCBS), Fixed Budget Based Selection (FBBS), Least Cost Based Selection (LCBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Opening of Financial Proposals / Minutes |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-119580-NC-RFP / Recruitment for External Auditor to Audit Project Financial Statements (PFSs) is to enable the auditor to express a professional opinion(s) on the financial position of the project at the end of each fiscal | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open - National | 100000 | Signed | Cleared | 2019/07/16 | 2019/06/17 | 2019/07/23 |  | 2019/08/06 | 2019/06/16 | 2019/08/20 | 2019/09/19 |  |  | 2019/08/20 |  | 2019/09/17 | 2019/07/24 | 2019/10/17 | 2019/09/19 | 2019/10/31 | 2019/09/27 | 2019/11/21 | 2019/09/27 | 2019/12/05 | 2019/10/04 | 2019/12/26 | 2019/11/07 |  | 2020/06/23
ET-MOLF-174092-CS-LCS / consultancy service for financial audit of LFSDP for the year 2012/13 EFY | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open - National | 100000 | Signed | Cleared | 2020/05/19 | 2020/06/16 | 2020/06/09 |  | 2020/07/09 | 2020/09/25 | 2020/07/23 | 2020/09/25 |  |  | 2020/07/23 |  | 2020/08/20 | 2020/09/25 | 2020/09/19 | 2020/09/25 | 2020/10/03 | 2020/10/12 | 2020/10/24 | 2020/10/12 | 2020/11/07 | 2020/10/27 | 2020/11/28 | 2020/10/31 |  | 2021/05/27
ET-MOLF-358673-CS-LCS / Procurement of Consulting services for feasibility study of Line of credit (LOC) Establishment for Sub-projects (CIGs, Cooperatives and Unions) of LFSDP. | No | IDA-61650 | Linking More Productive Farmers to Markets | Post | Consultant Services | Open - National | 100000 | Canceled | Modified/Cleared | 2023/05/03 |  | 2023/05/08 |  | 2023/05/28 |  | 2023/06/07 |  |  |  | 2023/06/07 |  | 2023/07/02 |  | 2023/07/12 |  | 2023/07/26 |  | 2023/08/10 |  | 2023/08/25 |  | 2023/09/09 |  |  | 2024/01/07
ET-MOLF-421196-CS-LCS / Consulting Services for External Financial Audit of 2016 and 2017 EFY | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 100000 | Signed | Cleared | 2024/04/11 | 2024/04/08 | 2024/04/21 |  | 2024/05/01 | 2024/04/12 | 2024/05/08 | 2024/05/09 |  |  | 2024/05/08 |  | 2024/05/29 | 2024/06/03 | 2024/06/08 | 2024/08/30 | 2024/06/18 | 2024/10/10 | 2024/06/28 | 2024/10/14 | 2024/07/12 | 2024/10/24 | 2024/07/22 | 2024/11/05 |  | 2024/10/20
ET-MOLF-288442-CS-LCS / Procurement of Consulting service for Financial Audit of LFSDP for the period of 2014/2015 EFY | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 150000 | Under Implementation | Cleared | 2022/04/13 | 2022/04/20 | 2022/04/18 |  | 2022/04/23 | 2022/04/15 | 2022/04/28 | 2022/04/20 |  |  | 2022/04/28 |  | 2022/05/23 | 2022/05/16 | 2022/06/07 | 2022/06/17 | 2022/06/17 | 2022/06/20 | 2022/07/02 | 2022/06/28 | 2022/07/17 |  | 2022/08/01 |  |  | 2022/09/30
ET-MOLF-400756-CS-QCBS / Procurement Consulting Service for End Line Survey of Livestock and Fisheries Sector Development Project | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 400000 | Under Implementation | Cleared | 2024/01/05 | 2024/03/01 | 2024/01/10 |  | 2024/01/12 | 2024/09/30 | 2024/01/22 | 2024/09/30 |  |  | 2024/01/22 |  | 2024/02/06 | 2024/11/18 | 2024/02/21 | 2024/12/25 | 2024/03/06 | 2025/01/09 | 2024/03/21 | 2025/01/13 | 2024/04/04 | 2025/01/18 | 2024/04/19 |  |  | 2024/06/18
ET-MOLF-82648-CS-QCBS / Consultancy services for data collection of 14 farming systems on Climate Smart Agriculture | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 70000 | Canceled | Cleared | 2018/12/09 |  | 2018/12/30 |  | 2019/01/29 |  | 2019/02/12 | [5 empty] | 2019/03/12 |  | 2019/04/11 |  | 2019/04/25 |  | 2019/05/16 |  | 2019/05/30 |  | 2019/06/20 |  |  | 2020/06/19
ET-MOLF-155488-CS-QCBS / Consultancy Service for Livestock and Fisheries Extension and Advisory Services (EAS) through the good animal husbandry practices (GAHP), good aquaculture and fisheries practices (GAFP) and Farmer Field School Approaches | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Consultant Services | Open - International | 1282558 | Canceled | Modified/Cleared | 2020/02/12 | 2020/05/20 | 2020/03/04 | 2020/06/16 | 2020/04/03 |  | 2020/04/17 |  |  |  | 2020/04/17 |  | 2020/05/15 |  | 2020/06/14 |  | 2020/06/28 |  | 2020/07/19 |  | 2020/08/02 |  | 2020/08/23 |  |  | 2021/08/23
ET-MOLF-285959-CS-QCBS / Consultancy Service for the Preparation and Implementation of the Fisheries and Aquaculture Master plan | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 670000 | Completed | Cleared | 2022/07/16 | 2022/08/02 | 2022/07/21 | 2022/08/09 | 2022/08/10 | 2022/10/10 | 2022/08/20 | 2022/10/13 |  |  | 2022/08/20 |  | 2022/10/09 | 2022/11/09 | 2022/10/19 | 2022/12/22 | 2022/10/24 | 2023/01/05 | 2022/11/13 | 2023/02/08 | 2022/11/23 | 2023/03/06 | 2022/12/08 | 2023/03/13 |  | 2023/08/05 | 2024/04/18
ET-MOLF-186846-CS-QCBS / Consultancy Service for the Preparation and Implementation of the Fisheries and Aquaculture Master plan | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 670000 | Canceled | Cleared | 2020/08/04 | 2020/08/02 | 2020/08/22 | 2020/09/09 | 2020/09/21 | 2021/04/02 | 2020/10/05 | 2021/04/08 |  |  | 2020/10/05 |  | 2020/11/02 | 2022/06/28 | 2020/12/02 |  | 2020/12/16 |  | 2021/01/06 |  | 2021/01/20 |  | 2021/02/10 |  |  | 2022/02/10
ET-MOLF-155496-CS-QCBS / Consultancy Service for the Performance recording in Diary Cattle and Terrestrial and Aquatic Animal Genetic Improvement | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 292061 | Canceled | Modified/Cleared | 2020/02/16 | 2020/02/26 | 2020/03/08 | 2020/04/28 | 2020/04/07 | 2020/06/22 | 2020/04/21 | 2020/09/25 |  |  | 2020/04/21 | 2020/09/25 | 2020/05/19 | 2020/10/27 | 2020/06/18 | 2020/10/27 | 2020/07/02 | 2020/11/17 | 2020/07/23 |  | 2020/08/06 |  | 2020/08/27 |  |  | 2021/08/27
ET-MOLF-213608-CS-QCBS / consultancy service for Independent Procurement Review | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open - International | 200000 | Canceled | Modified/Cleared | 2021/01/15 |  | 2021/02/05 |  | 2021/03/07 |  | 2021/03/21 |  |  |  | 2021/03/21 |  | 2021/04/18 |  | 2021/05/18 |  | 2021/06/01 |  | 2021/06/22 |  | 2021/07/06 |  | 2021/07/27 |  |  | 2022/07/27
ET-MOLF-285960-CS-QCBS / Consultancy Services for harmonization & integration, implementation and roll-out of Livestock Identification and Traceability System (LITS). | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 620000 | Canceled | Modified/Cleared | 2022/07/15 |  | 2022/07/20 |  | 2022/08/09 |  | 2022/08/14 |  |  |  | 2022/08/14 |  | 2022/10/03 |  | 2022/10/13 |  | 2022/10/28 |  | 2022/11/17 |  | 2022/12/02 |  | 2022/12/17 |  |  | 2023/07/15
ET-MOLF-82666-CS-QCBS / National Technical assistance for data management & analysis | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 100000 | Canceled | Cleared | 2018/10/18 |  | 2018/11/08 |  | 2018/12/08 |  | 2018/12/22 | [5 empty] | 2019/01/19 |  | 2019/02/18 |  | 2019/03/04 |  | 2019/03/25 |  | 2019/04/08 |  | 2019/04/29 |  |  | 2020/04/28
ET-MOLF-160178-CS-QCBS / Consultancy service for contract supervision of Holeta Bull-dam Farm Upgrading | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 97000 | Under Implementation | Cleared | 2020/02/27 | 2020/05/05 | 2020/03/19 |  | 2020/04/18 | 2020/05/29 | 2020/05/02 | 2020/06/02 |  |  | 2020/05/02 |  | 2020/05/30 | 2020/06/15 | 2020/06/29 | 2020/07/08 | 2020/07/13 | 2020/07/16 | 2020/08/03 | 2020/08/10 | 2020/08/17 | 2020/08/17 | 2020/09/07 |  |  | 2021/09/07
ET-MOLF-155498-CS-QCBS / Consultancy Service for the Preparation and Implementation of the Fisheries and Aquaculture Master plan | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 677291 | Canceled | Modified/Cleared | 2020/02/13 |  | 2020/03/05 |  | 2020/04/04 |  | 2020/04/18 |  |  |  | 2020/04/18 |  | 2020/05/16 |  | 2020/06/15 |  | 2020/06/29 |  | 2020/07/20 |  | 2020/08/03 |  | 2020/08/24 |  |  | 2021/08/24
ET-MOLF-139264-CS-QBS / Preparation of a plan for Tier2 GHG emission reporting in the livestock sector, including data collection and computation. | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open - National | 20000 | Canceled | Cleared | 2019/10/20 |  | 2019/11/10 |  | 2019/12/10 |  | 2019/12/24 |  |  |  | 2019/12/24 |  | 2020/01/21 |  | 2020/02/20 |  | 2020/03/05 |  | 2020/03/26 |  | 2020/04/09 |  | 2020/04/30 |  |  | 2021/04/30
ET-MOLF-155473-CS-QCBS / Consultancy Service of Technical Assistance for Data Analysis and Management System (DAMS) of Livestock & Fisheries. | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Consultant Services | Open - International | 1390000 | Canceled | Modified/Cleared | 2020/02/12 | 2020/07/29 | 2020/03/04 | 2020/07/30 | 2020/04/03 |  | 2020/04/17 |  |  |  | 2020/04/17 |  | 2020/05/15 |  | 2020/06/14 |  | 2020/06/28 |  | 2020/07/19 |  | 2020/08/02 |  | 2020/08/23 |  |  | 2021/08/23
ET-MOLF-155493-CS-QCBS / Consultancy Services for harmonization & integration, implementation and roll-out of Livestock Identification and Traceability System (LITS). | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 615000 | Canceled | Cleared | 2020/02/16 | 2020/05/14 | 2020/03/08 | 2020/04/28 | 2020/04/07 | 2020/06/10 | 2020/04/21 | 2020/06/16 |  |  | 2020/04/21 | 2020/07/24 | 2020/05/19 | 2022/06/28 | 2020/06/18 |  | 2020/07/02 |  | 2020/07/23 |  | 2020/08/06 |  | 2020/08/27 |  |  | 2021/08/27

## CQS
Consultant Qualification
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-82650-CS-QCBS / Prepare training materials (Trainer and Trainee Version on poultry,fishery,Dairy and Red meat | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 32000 | Canceled | Cleared | 2019/01/31 |  | 2019/02/21 |  | 2019/03/23 |  | 2019/04/06 |  | 2019/05/06 |  | 2019/05/20 |  | 2019/06/10 |  |  | 2019/12/07
ET-MOLF-82670-CS-QCBS / IT Training in software development & data base administration | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 23000 | Canceled | Cleared | 2018/12/04 |  | 2018/12/25 |  | 2019/01/24 |  | 2019/02/07 |  | 2019/03/09 |  | 2019/03/23 |  | 2019/04/13 |  |  | 2019/10/10
ET-MOLF-457203-CS-CQS / Procurement of Consulting Service for Independent Procurement Audit of LFSDP. | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - International | 200000 | Under Implementation | Cleared | 2024/11/15 | 2024/11/27 | 2024/11/20 | 2024/12/21 | 2024/12/04 |  | 2024/12/19 |  | 2025/01/03 |  | 2025/01/17 |  | 2025/02/07 |  |  | 2025/05/08
ET-MOLF-220702-CS-CQS / Technical Assistance of Consultancy Service for Midterm Survey | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open - International | 185000 | Completed | Cleared | 2021/02/21 | 2021/03/01 | 2021/02/23 | 2021/03/04 | 2021/03/10 | 2021/05/14 | 2021/03/12 | 2021/05/21 | 2021/03/16 | 2021/07/19 | 2021/03/18 | 2021/06/15 | 2021/03/22 | 2021/07/12 |  | 2021/09/15 | 2022/01/10
ET-MOLF-457203/2-CS-CQS / Procurement of Consulting Service for Independent Procurement Audit of LFSDP | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Consultant Services | Open - International | 200000 | Under Implementation | Cleared | 2024/11/15 | 2025/02/27 | 2024/12/13 |  | 2024/12/27 | 2025/04/02 | 2025/01/10 | 2025/04/16 | 2025/01/25 | 2025/07/18 | 2025/02/04 |  | 2025/02/19 |  |  | 2025/05/20

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-48662-CS-INDV / Recruitment of Project coordinator | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 15600 | Signed | Cleared | 2018/02/19 | 2018/03/19 | 2018/03/05 |  | 2018/03/20 | 2018/03/09 |  |  | 2018/03/25 | 2018/05/14 | 2018/04/08 | 2018/05/11 | 2018/04/22 | 2018/05/15 | 2018/05/06 | 2018/05/22 |  | 2019/05/01
ET-MOLF-82642-CS-INDV / Production of multiplication & translation of training manuals for L&F field workers | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 19525 | Canceled | Cleared | 2019/01/31 |  | 2019/02/14 |  | 2019/03/16 |  |  |  | 2019/03/21 |  | 2019/04/11 |  | 2019/04/25 |  | 2019/05/16 |  |  | 2019/11/12
ET-MOLF-465809-CS-INDV / Individual Consulting service for Environmental and Social Risk Framework Instruments of LFSDP II (Social Risk Management Specialist) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 15000 | Canceled | Cleared | 2024/12/23 |  | 2024/12/26 |  | 2025/01/09 |  |  |  | 2025/01/14 |  | 2025/01/24 |  | 2025/01/29 |  | 2025/02/03 |  |  | 2025/03/05
ET-MOLF-82668-CS-QCBS / Assessment of the current performance of Animal identification&recording system . | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 26000 | Canceled | Modified/Cleared | 2018/12/07 |  | 2018/12/21 |  | 2019/01/20 |  |  |  | 2019/01/25 |  | 2019/02/15 |  | 2019/03/01 |  | 2019/03/22 |  |  | 2019/09/18
ET-MOLF-479958-CS-INDV / Procurement of Social Safeguard Specialist; Individual Consulting Service for Social Safeguards Audit | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 9000 | Completed | Cleared | 2025/03/12 | 2025/04/04 | 2025/03/17 |  | 2025/03/31 | 2025/05/02 |  |  | 2025/04/05 | 2025/05/09 | 2025/04/15 | 2025/05/30 | 2025/04/23 | 2025/06/04 | 2025/05/03 | 2025/06/05 |  | 2025/06/12 | 2025/08/06
ET-MOLF-468253-CS-INDV / Individual Consulting service for hiring Environmental Risk Management Specialist for the preparation of Environmental and Social Risk Framework Instruments of LFSDP II | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Limited - National | 12000 | Signed | Cleared | 2024/12/27 | 2024/12/31 | [6 empty] | 2025/01/01 | 2025/02/05 | 2025/01/22 | 2025/02/05 | 2025/02/01 | 2025/02/12 | 2025/02/16 | 2025/02/12 |  | 2025/04/02
ET-MOLF-107917-CS-INDV / Recruitment project procurement specialist | No | IDA-61650 | Strengthening National Institutions and Programs | Prior | Consultant Services | Open | 10000 | Completed | Cleared | 2019/03/26 | 2019/06/12 | 2019/04/09 |  | 2019/05/09 | 2020/04/02 |  |  | 2019/05/14 | 2020/04/09 | 2019/06/04 | 2020/04/27 | 2019/06/18 | 2020/04/30 | 2019/07/09 | 2020/05/11 |  | 2020/01/05 | 2021/06/20
ET-MOLF-48664-CS-INDV / recruitment of Monitoring and evaluation specialist | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 12000 | Signed | Cleared | 2018/02/19 | 2018/02/20 | 2018/03/05 |  | 2018/03/19 | 2018/06/28 |  |  | 2018/03/24 | 2018/03/15 | 2018/04/07 | 2018/06/08 | 2018/04/21 |  | 2018/05/05 | 2018/06/21 |  | 2019/04/30
ET-MOLF-82672-CS-INDV / Update of national forage & feed dev. Program prepare investment plan | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 95000 | Canceled | Cleared | 2019/03/18 |  | 2019/04/01 |  | 2019/05/01 |  |  |  | 2019/05/06 |  | 2019/05/27 |  | 2019/06/10 |  | 2019/07/01 |  |  | 2019/12/28
ET-MOLF-48667-CS-INDV / Recruitment project procurement specialist | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 9600 | Signed | Cleared | 2018/02/19 | 2018/02/20 | 2018/03/05 |  | 2018/03/19 | 2018/05/04 |  |  | 2018/03/24 |  | 2018/04/07 | 2018/06/08 | 2018/04/21 |  | 2018/05/05 | 2018/06/17 |  | 2019/04/30
ET-MOLF-82637-CS-QCBS / Consultancy service for country need assessment on food safety | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 20000 | Canceled | Cleared | 2018/12/25 |  | 2019/01/08 |  | 2019/02/07 |  |  |  | 2019/02/12 |  | 2019/03/05 |  | 2019/03/19 |  | 2019/04/09 |  |  | 2019/10/06
ET-MOLF-479963-CS-INDV / Procurement of Environmental Safeguard Specialist; Individual Consulting Service for Environmental Safeguards Audit | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 9000 | Signed | Cleared | 2025/03/12 | 2025/04/04 | 2025/03/17 |  | 2025/03/31 | 2025/05/02 |  |  | 2025/04/05 | 2025/05/09 | 2025/04/10 | 2025/06/01 | 2025/04/20 | 2025/06/04 | 2025/04/30 | 2025/06/05 |  | 2025/06/09
ET-MOLF-468252-CS-INDV / Individual Consulting service for hiring Social Risk Management Specialist for the preparation of Environmental and Social Risk Framework Instruments of LFSDP II | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Limited - National | 16000 | Signed | Cleared | 2024/12/27 | 2024/12/31 | [6 empty] | 2025/01/01 | 2025/02/04 | 2025/01/22 | 2025/02/05 | 2025/02/01 | 2025/02/12 | 2025/02/11 | 2025/02/12 |  | 2025/03/28
ET-MOLF-48666-CS-INDV / recruitment of project financial specialist | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 12000 | Signed | Cleared | 2018/02/19 |  | 2018/03/05 |  | 2018/03/19 | 2018/05/25 |  |  | 2018/03/24 | 2018/06/11 | 2018/04/14 | 2018/06/08 | 2018/04/28 | 2018/06/07 | 2018/05/12 | 2018/05/28 |  | 2019/05/07
ET-MOLF-82653-CS-INDV / performance assessment of the sector based on the GTPII,LMP&FAMP | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 20000 | Canceled | Cleared | 2018/12/13 |  | 2018/12/27 |  | 2019/01/26 |  |  |  | 2019/01/31 |  | 2019/02/21 |  | 2019/03/07 |  | 2019/03/28 |  |  | 2019/09/24
ET-MOLF-82676-CS-INDV / support to feed & forage development units awareness & information activities | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 24000 | Canceled | Cleared | 2019/01/10 |  | 2019/01/24 |  | 2019/02/23 |  |  |  | 2019/02/28 |  | 2019/03/21 |  | 2019/04/04 |  | 2019/04/25 |  |  | 2019/10/22
ET-MOLF-213609-CS-INDV / Recruitment of project Environmental safeguard consultant | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 12500 | Under Implementation | Cleared | 2021/01/15 | 2021/02/16 | 2021/01/29 |  | 2021/02/28 | 2021/08/07 |  |  | 2021/03/05 | 2022/02/16 | 2021/03/26 |  | 2021/04/09 |  | 2021/04/30 |  |  | 2021/10/27
ET-MOLF-213610-CS-INDV / Recruitment of project social safeguard consultant | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Post | Consultant Services | Open | 100000 | Signed | Cleared | 2021/02/09 | 2022/02/21 | 2021/02/15 |  | 2021/03/11 | 2022/06/30 |  |  | 2021/03/16 | 2022/07/27 | 2021/04/01 | 2022/08/10 | 2021/04/15 | 2022/08/29 | 2021/04/29 | 2022/09/01 |  | 2021/06/30
ET-MOLF-465807-CS-INDV / Individual Consulting services for the preparation of Environmental and Social Risk Framework Instruments of LFSDP II (Environmental Risk Management Specialist) | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open - National | 11000 | Canceled | Cleared | 2024/12/23 |  | 2025/01/06 |  | 2025/01/11 |  |  |  | 2025/01/21 |  | 2025/01/26 |  | 2025/01/31 |  | 2025/02/10 |  |  | 2025/03/12
ET-MOLF-82639-CS-INDV / Consultancy services for capacity need assessment of NAHDIC and regional laboratories | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Open | 48000 | Canceled | Cleared | 2018/11/27 |  | 2018/12/11 |  | 2019/01/10 |  |  |  | 2019/01/15 |  | 2019/02/05 |  | 2019/02/19 |  | 2019/03/12 |  |  | 2019/09/08
ET-MOLF-233910-CS-INDV / Individual consulting service for Procurement Management Specialist | No | IDA-61650 | Project Coordination, Monitoring and Evaluation, and Knowledge Management | Prior | Consultant Services | Open | 25000 | Pending Implementation | Cleared | 2021/08/21 |  | 2021/08/27 |  | 2021/09/16 |  |  |  | 2021/09/22 |  | 2021/10/13 |  | 2021/10/25 |  | 2021/10/29 |  |  | 2022/10/28

## NPO - BANK - PRA
Non-Profit Organizations - Banks - Procurement Agents
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Short List and Draft Request for Proposals |  | Invitation to Identified / Selected Consultant |  | Amendments of Terms of Reference | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
ET-MOLF-103213-CS-UN / Baseline survey/by International Livestock Research institute/ | No | IDA-61650 | Strengthening National Institutions and Programs | Post | Consultant Services | Direct | 433000 | Signed | Cleared | 2019/03/14 | 2018/10/15 |  |  |  |  | 2019/03/19 | 2018/10/17 |  |  | 2019/03/24 | 2018/10/17 |  | 2019/04/23 | 2019/02/01 | 2019/05/07 | 2019/02/01 | 2019/05/28 | 2019/02/08 |  | 2019/11/24
ET-MOLF-103218-CS-UN / Up-scaling of small ruminant community-based breeding program in Ethiopia/ICARDA/ | No | IDA-61650 | Linking More Productive Farmers to Markets | Prior | Consultant Services | Direct | 556000 | Signed | Cleared | 2019/03/15 | 2019/09/09 |  |  |  |  | 2019/03/20 | 2019/10/10 |  |  | 2019/03/25 | 2019/05/01 |  | 2019/04/24 | 2019/12/04 | 2019/05/08 | 2019/12/21 | 2019/05/29 | 2019/12/05 |  | 2019/11/25